## Issues
Date | S.No | Description | Assigned To | Status | Check In Status | Satish Testing | TESTED BY
19/12 | 1 | LC Amend Request no is displaying as *******01-02 for second amendment | Kumar | Completed/Tested | CheckedIn | Working | NILAKANTHA
19/12 | 2 | LC Amend Request View displaying wrong results. Could be changed to display only details from the table. Rather than taking the entire record from chaincode(all tabs) | Kumar | Completed/Tested | CheckedIn | Working | NILAKANTHA
19/12 | 3 | After 2nd amendment, Version is still showing as version 1. Also reduce the font size of history dropdown | Kumar | Completed/Tested | CheckedIn | Working | NILAKANTHA
19/12 | 4 | Page is calling localhost:10009 continiously for no reason | Chandana | Completed/Tested | CheckedIn | Working | NILAKANTHA
19/12 | 5 | T24 reference id missing in BG Issue List | Varaprasad | Completed/Tested | CheckedIn | Working | NILAKANTHA
19/12 | 6 | Graph Indicator does not work in few cases. Eg. Attached | Varaprasad | Completed(To be Tested) | Not CheckedIn | Working | NILAKANTHA
19/12 | 7 | LC - Charges Tab. Ensure proper values for the CHARGE.ACCOUNT is retrieved, tested and scripts checked in | Chandana | Completed(To be Tested) | Not CheckedIn | Working | NILAKANTHA
19/12 | 8 | Deal Date should be removed from BG Issued Screen. Ensure validate button is working for business rules. Ensure the controls are aligned. Ensure it is removed in subseqent View & Approval pages | Nilkantha | Completed/Tested | CheckedIn
20/12 | 9 | Error when creating BG Open | Varaprasad | Completed/Tested | CheckedIn | Working (For First Tab only, First Tab+Charges)
20/12 | 10 | Sometimes, the screen shows like the attached.BG Request - Back button not working in BG Request Screen. LC Menu is missing | Varaprasad | Completed(To be Tested) | Not CheckedIn | Not Working
20/12 | 11 | Blocking issues | Nilkantha | Completed(To be Tested) | Not CheckedIn | Not Working
20/12 | 12 | Change header to Request Amend Bank Guarantee, Move the Buttons to the top panel (Same needs to be done on the BG Open Page as well) | Akshatha
20/12 | 13 | Tab names should be Proper case | Akshatha/Nilkantha | Completed(To be Tested) |  | Working | NILAKANTHA
20/12 | 14 | In case of errors in T24, display the error and make sure the status is not changed | Varaprasad | Completed(To be Tested) | Not CheckedIn | Working | NILAKANTHA
20/12 | 15 | BG Amend Request - Alignment Issues. Validations on Open Button | Akshatha
20/12 | 16 | Customer Home - Graph. Maximum value should be greater than | Varaprasad | Completed(To be Tested) | Not CheckedIn
20/12 | 17 | BG Amend Issues | Akshatha | Completed/Tested |  |  | NILAKANTHA
20/12 | 18 | BG Amend Request View | Akshatha | Completed/Tested |  |  | NILAKANTHA
20/12 | 19 | Accept BG Amend Request | Akshatha | Completed/Tested |  |  | NILAKANTHA
20/12 | 20 | BG Issue View | VP/Akshatha | Completed/Tested |  |  | NILAKANTHA
20/12 | 21 | Approve Amend | Akshatha | Completed/Tested |  |  | NILAKANTHA
20/12 | 22 | BG View Issues | Akshatha |  |  |  | NILAKANTHA
20/12 | 23 | Emailer Issues | Akshatha
20/12 | 24 | Enable / Disable of Buttons | Akshatha | Completed/Tested |  |  | NILAKANTHA
20/12 | 25 | Counterparty is unable to view opened BG records | Akshatha |  |  |  | NILAKANTHA
21/12 | 26 | Graph does not load | Chandana
21/12 | 27 | Wrong View for LC Amend Request (For Employee) | Kumar | Completed/Tested |  |  | NILAKANTHA
21/12 | 28 | Validation should work for BG Request button also | Varaprasad | Completed/Tested |  |  | NILAKANTHA
21/12 | 29 | Commision Frequency on the LC Open / BG Issued. What is the resolution? | Chandana |  |  |  | NILAKANTHA
21/12 | 30 | Details of what fields should have what values for commision tab on the BG Issue Screen. Check for all fields | Varaprasad |  |  |  | NILAKANTHA
21/12 | 31 | View Request BG - takes to login page | Varaprasad | Completed/Tested |  |  | NILAKANTHA
21/12 | 32 | LC Open - Charges Tab values are not appearing in T24. Commision amount is not reflected | Chandana | Completed/Tested |  |  | NILAKANTHA

## Sheet1
Date | S.No | Description | Assigned To | Status | Check In Status | Satish Testing
19/12 | 8 | Deal Date should be removed from BG Issued Screen. Ensure validate button is working for business rules. Ensure the controls are aligned. Ensure it is removed in subseqent View & Approval pages | Nilkantha | Completed(To be Tested) | CheckedIn | Working
20/12 | 11 | Blocking issues | Nilkantha | Completed(To be Tested) | CheckedIn | Working

## 1
COMPLETED

## 2
COMPLETED

## 3
COMPLETED

## 4
COMPLETED

## 5
COMPLETED

## 6
6

## 8
COMPLETED

## 9
requestBody====>>> <soapenv:Envelope xmlns:soapenv="http://schemas.xmlsoap.org/soap/envelope/" xmlns:bgis="http://temenos.com/BgIssue" xmlns:mdd="http://temenos.com/MDDEALGTISS1"><soapenv:Header/><soa
penv:Body><bgis:BgIssue><!--Optional:--><WebRequestCommon><!--Optional:--><company>GB0010001</company><password>123123</password><userName>INPUTT</userName></WebRequestCommon><!--Optional:--><OfsFunct
ion><!--Optional:--><activityName></activityName><!--Optional:--><assignReason></assignReason><!--Optional:--><dueDate></dueDate><!--Optional:--><extProcess></extProcess><!--Optional:--><extProcessID>
</extProcessID><!--Optional:--><gtsControl></gtsControl><!--Optional:--><messageId></messageId><!--Optional:--><noOfAuth></noOfAuth><!--Optional:--><owner></owner><!--Optional:--><replace></replace><!
--Optional:--><startDate></startDate><!--Optional:--><user></user></OfsFunction><!--Optional:--><MDDEALGTISS1Type id=""><!--Optional:--><mdd:CUSTOMER>100266</mdd:CUSTOMER><!--Optional:--><mdd:CURRENCY
>USD</mdd:CURRENCY><!--Optional:--><mdd:PRINCIPALAMOUNT>1000000</mdd:PRINCIPALAMOUNT><!--Optional:--><mdd:DEALDATE></mdd:DEALDATE><!--Optional:--><mdd:VALUEDATE>20171219</mdd:VALUEDATE><!--Optional:--
><mdd:MATURITYDATE>20171221</mdd:MATURITYDATE><!--Optional:--><mdd:CONTRACTTYPE></mdd:CONTRACTTYPE><!--Optional:--><mdd:DEALSUBTYPE></mdd:DEALSUBTYPE><!--Optional:--><mdd:CATEGORY></mdd:CATEGORY><!--O
ptional:--><mdd:LIMITREFERENCE></mdd:LIMITREFERENCE><!--Optional:--><mdd:gCHARGEDATE g="1"><!--Zero or more repetitions:--><mdd:mCHARGEDATE m="1"><!--Optional:--><mdd:CHARGEDATE></mdd:CHARGEDATE><!--O
ptional:--><mdd:CHARGECURR></mdd:CHARGECURR><!--Optional:--><mdd:CHARGEACCOUNT></mdd:CHARGEACCOUNT><!--Optional:--><mdd:sgCHARGECODE sg="1"><!--Zero or more repetitions:--><mdd:CHARGECODE s="1"><!--Op
tional:--><mdd:CHARGECODE></mdd:CHARGECODE><!--Optional:--><mdd:CHARGEAMT></mdd:CHARGEAMT></mdd:CHARGECODE></mdd:sgCHARGECODE></mdd:mCHARGEDATE></mdd:gCHARGEDATE><!--Optional:--><mdd:gBENEFCUST1 g="1"
><!--Zero or more repetitions:--><mdd:BENEFCUST1>100111</mdd:BENEFCUST1></mdd:gBENEFCUST1><!--Optional:--><mdd:REFERENCE2>CRREF</mdd:REFERENCE2><!--Optional:--><mdd:gTEXT1 g="1"><!--Zero or more repet
itions:--><mdd:TEXT1>TEST</mdd:TEXT1></mdd:gTEXT1><!--Optional:--><mdd:gBENADDRESS g="1"><!--Zero or more repetitions:--><mdd:BENADDRESS>ALPHABank</mdd:BENADDRESS></mdd:gBENADDRESS><!--Optional:--><md
d:CSNPAYMENTTYPE></mdd:CSNPAYMENTTYPE><!--Optional:--><mdd:ACCRUALPARAM></mdd:ACCRUALPARAM><!--Optional:--><mdd:INTERESTBASIS></mdd:INTERESTBASIS><!--Optional:--><mdd:CSNRATE></mdd:CSNRATE><!--Optiona
l:--><mdd:CSNSPREAD></mdd:CSNSPREAD><!--Optional:--><mdd:CURRENTRATE></mdd:CURRENTRATE><!--Optional:--><mdd:FIXEDAMOUNT></mdd:FIXEDAMOUNT><!--Optional:--><mdd:CSNFREQUENCY></mdd:CSNFREQUENCY><!--Optio
nal:--><mdd:gCSNDATE g="1"><!--Zero or more repetitions:--><mdd:mCSNDATE m="1"><!--Optional:--><mdd:CSNDATE></mdd:CSNDATE><!--Optional:--><mdd:CSNAMOUNT></mdd:CSNAMOUNT><!--Optional:--><mdd:CSNACCOUNT
></mdd:CSNACCOUNT><!--Optional:--><mdd:CONVERSIONRATE></mdd:CONVERSIONRATE></mdd:mCSNDATE></mdd:gCSNDATE><!--Optional:--><mdd:ISSUECUSTOMER></mdd:ISSUECUSTOMER><!--Optional:--><mdd:gPARTICIPANT g="1">
<!--Zero or more repetitions:--><mdd:mPARTICIPANT m="1"><!--Optional:--><mdd:PARTICIPANT></mdd:PARTICIPANT><!--Optional:--><mdd:AMTPARTICIPATE></mdd:AMTPARTICIPATE></mdd:mPARTICIPANT></mdd:gPARTICIPAN
T><!--Optional:--><mdd:NETPRINAMOUNT></mdd:NETPRINAMOUNT><!--Optional:--><mdd:PROVISION></mdd:PROVISION><!--Optional:--><mdd:PROVDRACCOUNT></mdd:PROVDRACCOUNT><!--Optional:--><mdd:PROVPERCENT></mdd:PR
OVPERCENT><!--Optional:--><mdd:PROVAMOUNT></mdd:PROVAMOUNT><!--Optional:--><mdd:PROVCRACCOUNT></mdd:PROVCRACCOUNT><!--Optional:--><mdd:PROVRELDATE></mdd:PROVRELDATE><!--Optional:--><mdd:PROVRELACCOUNT
></mdd:PROVRELACCOUNT><!--Optional:--><mdd:AUTOEXPIRY>No</mdd:AUTOEXPIRY><!--Optional:--><mdd:ALTERNATEID>GRREF</mdd:ALTERNATEID><!--Optional:--><mdd:LIQUIDATIONMODE>Manual</mdd:LIQUIDATIONMODE><!--Op
tional:--><mdd:EVENTSPROCESSING>Online</mdd:EVENTSPROCESSING><!--Optional:--><mdd:SLREFTRANCHE></mdd:SLREFTRANCHE><!--Optional:--><mdd:SLPRODTYPE></mdd:SLPRODTYPE><!--Optional:--><mdd:SLLINKDATE></mdd
:SLLINKDATE><!--Optional:--><mdd:RATECHANGE></mdd:RATECHANGE><!--Optional:--><mdd:NEWCSNRATE></mdd:NEWCSNRATE><!--Optional:--><mdd:NEWRATEEFFDATE></mdd:NEWRATEEFFDATE><!--Optional:--><mdd:RETURNCOMM><
/mdd:RETURNCOMM><!--Optional:--><mdd:ADVICEEXPIRYDATE>20171220</mdd:ADVICEEXPIRYDATE><!--Optional:--><mdd:PROVEXCHRATE></mdd:PROVEXCHRATE><!--Optional:--><mdd:CSNCLAIM></mdd:CSNCLAIM></MDDEALGTISS1Typ
e></bgis:BgIssue></soapenv:Body></soapenv:Envelope>
test1----->>>>>>> {"S:Envelope":{"$":{"xmlns:S":"http://schemas.xmlsoap.org/soap/envelope/"},"S:Body":[{"ns4:BgIssueResponse":[{"$":{"xmlns:ns4":"http://temenos.com/BgIssue","xmlns:ns3":"http://temeno
s.com/MDDEALGTISS1","xmlns:ns2":"http://temenos.com/MDDEAL"},"Status":[{"transactionId":["MD1511222217"],"messageId":[""],"successIndicator":["T24Error"],"application":["NO"],"messages":["AUTO.EXPIRY:
1:1=NO SPECIFIED VALUE"]}]}]}]}}
test------>>>>>>>> { 'S:Envelope':
{ '$': { 'xmlns:S': 'http://schemas.xmlsoap.org/soap/envelope/' },
'S:Body': [ [Object] ] } }
transactionId [ 'MD1511222217' ]
TransactionID MD1511222217
COMPLETED

## 11
[ibc-js] GetCustomerBasedRecords - success: { jsonrpc: '2.0', result: { status: 'OK' }, id: 1513686723336 }

## 17
Date control for BG Expiry date
BG Amend Request No in single row
No of amendments in single row
Make MT 760 instead of mt760
COMPLETED

## 18
BG Amend Request No in single row
No of amendments in single row
COMPLETED

## 19
BG Amend Request No in single row
No of amendments in single row
Make MT 760 instead of mt760
COMPLETED

## 20
Try to fit in to single row (both heading and details)
History column. Drop down .. reduce the font size
COMPLETED

## 21
BG Amend Request No in single row
No of amendments in single row
Make MT 760 instead of mt760
COMPLETED

## 22
This exists in customer page only.
Instead of version 2 version should appear
Both initial and version2 giving same result

## 23
Emailer Error
request body============>>>>> { bgNumber_t1: 'BG-241660939577',
bgAmendReqId: 'BG-241660939577-002',
amount_t1: '1350000',
termsNconditions_1_t1: 'tettt',
expiryDate_t1: '12/24/2017',
bgNumberOfAmendments: 2,
status: 'AMENDED' }
updated of record bgAmendReqId: BG-241660939577-002
updated of record:bgAmendId BG-241660939577
TypeError: Cannot read property 'toLowerCase' of undefined
at Object.handle (D:\Users\akshag\Desktop\TF_latest_1219\appOriginal.js:1274:36)
at next_layer (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\route.js:103:13)
at Route.dispatch (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\route.js:107:5)
at D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:195:24
at Function.proto.process_params (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:251:12)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:189:19)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)

## 24
Enable / Disable Approve and Amend Approve button
COMPLETED

## 25
Counterparty is unable to view the records of BG opened

## 27
COMPLETED

## 28
COMPLETED

## 31
RESOLVED

## 32
COMPLETED