## Issues
Date | S.No | Description | Assigned To | Status | Check In Status | Satish Testing | TESTED BY
19/12 | 1 | LC Amend Request no is displaying as *******01-02 for second amendment | Kumar | Completed | Done | Working | CHANDANA
19/12 | 2 | LC Amend Request View displaying wrong results. Could be changed to display only details from the table. Rather than taking the entire record from chaincode(all tabs) | Kumar | Completed | Done | Working | CHANDANA
19/12 | 3 | After 2nd amendment, Version is still showing as version 1. Also reduce the font size of history dropdown | Kumar | Completed | Done | Working | CHANDANA
19/12 | 4 | Page is calling localhost:10009 continiously for no reason | Chandana | Completed | Done | Working | NILAKANTHA
19/12 | 5 | T24 reference id missing in BG Issue List | Varaprasad | Completed | Done | Working | NILAKANTHA
19/12 | 6 | Graph Indicator does not work in few cases. Eg. Attached | Varaprasad | Completed | Done | Working | CHANDANA
19/12 | 7 | LC - Charges Tab. Ensure proper values for the CHARGE.ACCOUNT is retrieved, tested and scripts checked in | Chandana | Completed | Done | Working | CHANDANA
19/12 | 8 | Deal Date should be removed from BG Issued Screen. Ensure validate button is working for business rules. Ensure the controls are aligned. Ensure it is removed in subseqent View & Approval pages | Nilkantha | Completed | Done | Working | NILAKANTHA
20/12 | 9 | Error when creating BG Open | Varaprasad | Completed | Done | Working | NILAKANTHA
20/12 | 10 | Sometimes, the screen shows like the attached.BG Request - Back button not working in BG Request Screen. LC Menu is missing | Varaprasad | Completed | Done | Working | NILAKANTHA
20/12 | 11 | Blocking issues | Nilkantha | Completed | Done | Working | NILAKANTHA
20/12 | 12 | Change header to Request Amend Bank Guarantee, Move the Buttons to the top panel (Same needs to be done on the BG Open Page as well) | Akshatha | Completed | Done | Working | NILAKANTHA
20/12 | 13 | Tab names should be Proper case | Akshatha/Nilkantha | Completed | Done | Working | NILAKANTHA
20/12 | 14 | In case of errors in T24, display the error and make sure the status is not changed | Varaprasad | Completed | Done | Working | NILAKANTHA
20/12 | 15 | BG Amend Request - Alignment Issues. Validations on Open Button | Akshatha | Completed | Done | Working | NILAKANTHA
20/12 | 16 | Customer Home - Graph. Maximum value should be greater than | Varaprasad | Completed | Done |  | CHANDANA
20/12 | 17 | BG Amend Issues | Akshatha | Completed | Done | Working | NILAKANTHA
20/12 | 18 | BG Amend Request View | Akshatha | Completed | Done | Working | NILAKANTHA
20/12 | 19 | Accept BG Amend Request | Akshatha | Completed | Done | Working | NILAKANTHA
20/12 | 20 | BG Issue View | VP/Akshatha | Completed | Done | Working | NILAKANTHA
20/12 | 21 | Approve Amend | Akshatha | Completed | Done | Working | NILAKANTHA
20/12 | 22 | BG View Issues | Akshatha | Completed | Done | Working | NILAKANTHA
20/12 | 23 | Emailer Issues | Akshatha | Completed | Done | Working | NILAKANTHA
20/12 | 24 | Enable / Disable of Buttons | Akshatha | Completed | Done | Working | NILAKANTHA
20/12 | 25 | Counterparty is unable to view opened BG records | Akshatha | Completed | Done | Working | NILAKANTHA
21/12 | 26 | Graph does not load | Chandana | Completed | Done | Working | CHANDANA
21/12 | 27 | Wrong View for LC Amend Request (For Employee) | Kumar | Completed | Done | Working | CHANDANA
21/12 | 28 | Validation should work for BG Request button also | Varaprasad | Completed | Done | Working | NILAKANTHA
21/12 | 29 | Commision Frequency on the LC Open / BG Issued. What is the resolution? | Varaprasad | Not Completed | Done | Working | NILAKANTHA
21/12 | 30 | Details of what fields should have what values for commision tab on the BG Issue Screen. Check for all fields | Varaprasad | Completed | Done | Working | NILAKANTHA
21/12 | 31 | View Request BG - takes to login page | Varaprasad | Completed | Done | Working | NILAKANTHA
21/12 | 32 | LC Open - Charges Tab values are not appearing in T24. Commision amount is not reflected | Chandana | Completed | Done | Working | CHANDANA
| 33 | LC - File Upload should be made optional. Also, do not show error in case the file is not uploaded. | Kumar | Completed |  |  | CHANDANA
| 34 | LC Shipment Date - Missing in the View (Value not appearing) | Kumar | Completed |  |  | CHANDANA
| 35 | File Download - File Name (word file) (JPEG/JPG,PNG,PDF,DOC,DOCX - Apply filters) - VALIDATION needs to be implemented | Kumar | Completed |  |  | CHANDANA
| 36 | Employee Home - Make BG graph dynamic | Chandana | Completed |  |  | CHANDANA
| 37 | LC AMend Request - Alignment | Varaprasad | Completed | Done | Working | NILAKANTHA
| 38 | Enable / Disable button for LC Open List Page (START FROM 10007 and ) | Kumar | Completed |  |  | CHANDANA
| 39 | LC - Opening - With Charges (only two fields are sent to T24) | Chandana | Check with Veni |  |  | CHANDANA
| 40 | LC Opening - With Commision (Account was not passed) | Chandana | Check with Veni |  |  | CHANDANA
| 41 | Issue No. 16 not fixed - PROVIDE EVIDENCE | Varaprasad | Completed | Done |  | NILAKANTHA
| 42 | Issue No. 5 not fixed (Doesn’t see to be correct) - PROVIDE EVIDENCE | Varaprasad | Completed | Done |  | NILAKANTHA
| 43 | BG - Charges and Commision - Check whether None or (empty) should be passed for checkboxes - Option 1 not working - PROVIDE EVIDENCE | Varaprasad | Completed | Done |  | NILAKANTHA
| 44 | Charges and Commision details are not displayed in UI from chaincode. (Check View & Accept Page as well) | Nilkantha | Completed |  |  | NILAKANTHA
| 45 | Remove unnecessary files from repository | Akshatha |  |  |  | NILAKANTHA
| 46 | back button not working in bg amend and alignment | Varaprasad | Completed |  |  | NILAKANTHA
|  | lc amend page alignmnt | Varaprasad | Completed | Done |  | CHANDANA
| 47 | Customer Home Page – Notification panel - Menu gets overwritten by display results panel (use percentage instead of a fixed number) | Varaprasad | Completed | Done |  | CHANDANA
| 48 | Customer Home – LC Request List View – Menu gets overwritten by display results panel (use percentage instead of a fixed number) | Varaprasad | Completed | Done |  | CHANDANA
| 49 | Customer Home – LC Open List View – Menu gets overwritten by display results panel (use percentage instead of a fixed number) | Varaprasad | Completed | Done |  | CHANDANA
| 50 | Customer Home – LC Request View – Menu gets overwritten by display results panel (use percentage instead of a fixed number) | Varaprasad | Completed | Done |  | CHANDANA
| 51 | Customer Home – BG Request List View – Menu gets overwritten by display results panel (use percentage instead of a fixed number) | Varaprasad | Completed | Done |  | NILAKANTHA
| 52 | Customer Home – BG Request List View – Menu gets overwritten by display results panel (use percentage instead of a fixed number) | Varaprasad | Completed | Done |  | NILAKANTHA
| 53 | Customer Home – LC Amend Request View – Menu gets overwritten by display results panel (use percentage instead of a fixed number) | Varaprasad | Completed | Done |  | CHANDANA
| 54 | Employee Home – LC Request View – Menu gets overwritten by display results panel (use percentage instead of a fixed number) | Varaprasad | Completed | Done |  | NILAKANTHA
| 55 | Employee Home – BG Issue – Alignment of Liquidation Mode, Remove space in between tab and the page header. | Varaprasad | Completed |  |  | NILAKANTHA
| 56 | Employee Home – BG Request List View - Remove background color under BG actions. Change the View button to look like Accept Amend | Varaprasad | Completed | Done |  | NILAKANTHA
| 57 | Employee Home – BG Issue List View a. – Remove background color below History, b. Left Align the column header c. Change “All Bank Guarantee” to “Bank Guarantee – Issued” | Varaprasad | Completed | Done |  | NILAKANTHA
| 58 | Customer Home – BG Requested View a. Change “All Bank Guarantee” to “Bank Guarantee – Requested” | Varaprasad | Completed | Done |  | NILAKANTHA
| 59 | Employee Home – BG Requested View a. Change “All Bank Guarantee” to “Bank Guarantee – Requested” b. Add status | Varaprasad | Completed | Done |  | NILAKANTHA
| 60 | Customer Home – BG Request List (Amendment) a. Change the view button style | Varaprasad | Completed | Done |  | NILAKANTHA
| 61 | Employee Home – BG Issued Left Alignment for the column header | Varaprasad | Completed | Done |  | NILAKANTHA
| 62 | In Customer Home and Employee Home Page a. Requested List b. Opened (Issued) List Make the column header color as grey and details should be in white. Also buttons on Actions should have background color as grey. Ensure the buttons under action are middle aligned. Check the look and feel of list pages are uniform | Varaprasad | Completed | Done |  | NILAKANTHA
| 63 | lc amend back button not working | Varaprasad | Completed | Done |  | CHANDANA
| 64 | lc open page capgemini logo old one--remove logo | Varaprasad | Completed | Done |  | CHANDANA
| 65 | lc amend approve-- back button not working | Varaprasad | Completed |  |  | CHANDANA
| 66 | bgAmendReq view header alignment missing | Varaprasad | Completed | Done |  | NILAKANTHA
| 67 | lc Amend accept lc dropdown requested/opened view redirecting to login page. It should be redirected to whatever the user has selected | Varaprasad | Completed |  |  | CHANDANA
| 68 | lc Amend approve lc dropdown requested/opened view redirecting to login page | Varaprasad | Completed |  |  | CHANDANA
| 69 | lc accept/approve page expiry date format is wrong | Varaprasad | Completed | Done |  | CHANDANA
| 70 | deal date should be removed from approve page and alignment | Varaprasad | Completed | Done |  | NILAKANTHA
| 71 | deal date should be removed from amend approve | Varaprasad | Completed | Done |  | NILAKANTHA
| 72 | When no image is uploaded, chaincode should not have the image and handle it in the View(Request View & Open View), Open, Approve pages | Kumar | Completed |  |  | CHANDANA
| 73 | Customer Home - LC Request List View - Amend Request View - Remove space between two rows (Similar to BG Amend Request List) | Varaprasad | Completed | Done |  | CHANDANA
| 74 | Employee Home - LC Request List View - Request & Amend Request Records - Remove space between two rows (Similar to BG Amend Request List) | Varaprasad | Completed | Done |  | NILAKANTHA
| 75 | Customer Home - BG Open List View -> BG Amend button->Spacing,Deal Date and Alignment Issues; View button -> Spacing Issues | Varaprasad | Completed | Done |  | NILAKANTHA
| 76 | Customer Home - BG Open List View - Remove space between two rows (Similar to BG Amend Request List) | Varaprasad | Completed | Done |  | NILAKANTHA
| 77 | Employee Home - Home Page some details missing like - No of BG expiring and BG Opening option is not available | Chandana | Completed |  |  | NILAKANTHA
| 78 | Issue No 35 not working. It fails when a invalid file type is selected and tried to submit the record directly (without uploading) | Kumar | Completed |  |  | NILAKANTHA
| 79 | LC - Opening from 10007 (appOriginal1.js) does not send it to T24 | Varaprasad | Completed |  |  | CHANDANA
| 80 | Comment the below line in appOriginal.js file and appOriginal1.js function (lc-open) chaincode.invoke.UpdateTransactionId([ID, TransactionID]); function (bg-open) chaincode.invoke.UpdateBgTransactionId([ID, TransactionID]); | Kumar | Completed |  |  | CHANDANA
| 81 | Bills downloaded are not displaying the proper file type | Akshatha |  |  |  | NILAKANTHA
| 82 | Unable to do verify and Bill Input for LC (ie buttons are disabled) | Akshatha | Completed |  |  | NILAKANTHA
| 83 | Enable / Disable of BG Issued Records (Approve button is always enabled) | Akshatha | Completed |  |  | NILAKANTHA
| 84 | Values for Auto Expiry, Event Processing and Liquadation mode are not appearing in Amend Request | Varaprasad | Completed |  |  | NILAKANTHA
| 85 | BG Amend -> User Selecting View BG Requested-> Redirecting to Login Screen | Varaprasad | Completed |  |  | NILAKANTHA
| 86 | BG Amend -> User Selecting View Issued BG -> Redirecting to Login Screen | Varaprasad | Completed |  |  | NILAKANTHA
| 87 | LC - Request, LC Amend Request - Users should not view others record | Varaprasad | Completed |  |  | CHANDANA
| 88 | BG - Request, BG Amend Request - Users should not view others record | Varaprasad | Completed |  |  | NILAKANTHA
| 89 | LC Amend Request - Applicant ID(Customer ID) has to be saved in Table. Add a field Applicant ID | Kumar | Completed |  |  | CHANDANA
| 90 | BG Amend Request - Applicant ID(Customer ID) has to be saved in Table. Add a field Applicant ID | Akshatha | Completed |  |  | NILAKANTHA
| 91 | lc amend approve expiry date format wrong | Varaprasad | Completed |  |  | CHANDANA

## 79
second record is created in 10007 - employee home

## 25
Counterparty is unable to view the records of BG opened

## 24
Enable / Disable Approve and Amend Approve button

## 23
Emailer Error
request body============>>>>> { bgNumber_t1: 'BG-241660939577',
bgAmendReqId: 'BG-241660939577-002',
amount_t1: '1350000',
termsNconditions_1_t1: 'tettt',
expiryDate_t1: '12/24/2017',
bgNumberOfAmendments: 2,
status: 'AMENDED' }
updated of record bgAmendReqId: BG-241660939577-002
updated of record:bgAmendId BG-241660939577
TypeError: Cannot read property 'toLowerCase' of undefined
at Object.handle (D:\Users\akshag\Desktop\TF_latest_1219\appOriginal.js:1274:36)
at next_layer (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\route.js:103:13)
at Route.dispatch (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\route.js:107:5)
at D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:195:24
at Function.proto.process_params (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:251:12)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:189:19)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)
at next (D:\Users\akshag\Desktop\TF_latest_1219\node_modules\express\lib\router\index.js:166:38)

## 22
This exists in customer page only.
Instead of version 2 version should appear
Both initial and version2 giving same result

## 21
BG Amend Request No in single row
No of amendments in single row
Make MT 760 instead of mt760

## 20
Try to fit in to single row (both heading and details)
History column. Drop down .. reduce the font size

## 19
BG Amend Request No in single row
No of amendments in single row
Make MT 760 instead of mt760

## 18
BG Amend Request No in single row
No of amendments in single row

## 17
Date control for BG Expiry date
BG Amend Request No in single row
No of amendments in single row
Make MT 760 instead of mt760

## 6
6

## 9
requestBody====>>> <soapenv:Envelope xmlns:soapenv="http://schemas.xmlsoap.org/soap/envelope/" xmlns:bgis="http://temenos.com/BgIssue" xmlns:mdd="http://temenos.com/MDDEALGTISS1"><soapenv:Header/><soa
penv:Body><bgis:BgIssue><!--Optional:--><WebRequestCommon><!--Optional:--><company>GB0010001</company><password>123123</password><userName>INPUTT</userName></WebRequestCommon><!--Optional:--><OfsFunct
ion><!--Optional:--><activityName></activityName><!--Optional:--><assignReason></assignReason><!--Optional:--><dueDate></dueDate><!--Optional:--><extProcess></extProcess><!--Optional:--><extProcessID>
</extProcessID><!--Optional:--><gtsControl></gtsControl><!--Optional:--><messageId></messageId><!--Optional:--><noOfAuth></noOfAuth><!--Optional:--><owner></owner><!--Optional:--><replace></replace><!
--Optional:--><startDate></startDate><!--Optional:--><user></user></OfsFunction><!--Optional:--><MDDEALGTISS1Type id=""><!--Optional:--><mdd:CUSTOMER>100266</mdd:CUSTOMER><!--Optional:--><mdd:CURRENCY
>USD</mdd:CURRENCY><!--Optional:--><mdd:PRINCIPALAMOUNT>1000000</mdd:PRINCIPALAMOUNT><!--Optional:--><mdd:DEALDATE></mdd:DEALDATE><!--Optional:--><mdd:VALUEDATE>20171219</mdd:VALUEDATE><!--Optional:--
><mdd:MATURITYDATE>20171221</mdd:MATURITYDATE><!--Optional:--><mdd:CONTRACTTYPE></mdd:CONTRACTTYPE><!--Optional:--><mdd:DEALSUBTYPE></mdd:DEALSUBTYPE><!--Optional:--><mdd:CATEGORY></mdd:CATEGORY><!--O
ptional:--><mdd:LIMITREFERENCE></mdd:LIMITREFERENCE><!--Optional:--><mdd:gCHARGEDATE g="1"><!--Zero or more repetitions:--><mdd:mCHARGEDATE m="1"><!--Optional:--><mdd:CHARGEDATE></mdd:CHARGEDATE><!--O
ptional:--><mdd:CHARGECURR></mdd:CHARGECURR><!--Optional:--><mdd:CHARGEACCOUNT></mdd:CHARGEACCOUNT><!--Optional:--><mdd:sgCHARGECODE sg="1"><!--Zero or more repetitions:--><mdd:CHARGECODE s="1"><!--Op
tional:--><mdd:CHARGECODE></mdd:CHARGECODE><!--Optional:--><mdd:CHARGEAMT></mdd:CHARGEAMT></mdd:CHARGECODE></mdd:sgCHARGECODE></mdd:mCHARGEDATE></mdd:gCHARGEDATE><!--Optional:--><mdd:gBENEFCUST1 g="1"
><!--Zero or more repetitions:--><mdd:BENEFCUST1>100111</mdd:BENEFCUST1></mdd:gBENEFCUST1><!--Optional:--><mdd:REFERENCE2>CRREF</mdd:REFERENCE2><!--Optional:--><mdd:gTEXT1 g="1"><!--Zero or more repet
itions:--><mdd:TEXT1>TEST</mdd:TEXT1></mdd:gTEXT1><!--Optional:--><mdd:gBENADDRESS g="1"><!--Zero or more repetitions:--><mdd:BENADDRESS>ALPHABank</mdd:BENADDRESS></mdd:gBENADDRESS><!--Optional:--><md
d:CSNPAYMENTTYPE></mdd:CSNPAYMENTTYPE><!--Optional:--><mdd:ACCRUALPARAM></mdd:ACCRUALPARAM><!--Optional:--><mdd:INTERESTBASIS></mdd:INTERESTBASIS><!--Optional:--><mdd:CSNRATE></mdd:CSNRATE><!--Optiona
l:--><mdd:CSNSPREAD></mdd:CSNSPREAD><!--Optional:--><mdd:CURRENTRATE></mdd:CURRENTRATE><!--Optional:--><mdd:FIXEDAMOUNT></mdd:FIXEDAMOUNT><!--Optional:--><mdd:CSNFREQUENCY></mdd:CSNFREQUENCY><!--Optio
nal:--><mdd:gCSNDATE g="1"><!--Zero or more repetitions:--><mdd:mCSNDATE m="1"><!--Optional:--><mdd:CSNDATE></mdd:CSNDATE><!--Optional:--><mdd:CSNAMOUNT></mdd:CSNAMOUNT><!--Optional:--><mdd:CSNACCOUNT
></mdd:CSNACCOUNT><!--Optional:--><mdd:CONVERSIONRATE></mdd:CONVERSIONRATE></mdd:mCSNDATE></mdd:gCSNDATE><!--Optional:--><mdd:ISSUECUSTOMER></mdd:ISSUECUSTOMER><!--Optional:--><mdd:gPARTICIPANT g="1">
<!--Zero or more repetitions:--><mdd:mPARTICIPANT m="1"><!--Optional:--><mdd:PARTICIPANT></mdd:PARTICIPANT><!--Optional:--><mdd:AMTPARTICIPATE></mdd:AMTPARTICIPATE></mdd:mPARTICIPANT></mdd:gPARTICIPAN
T><!--Optional:--><mdd:NETPRINAMOUNT></mdd:NETPRINAMOUNT><!--Optional:--><mdd:PROVISION></mdd:PROVISION><!--Optional:--><mdd:PROVDRACCOUNT></mdd:PROVDRACCOUNT><!--Optional:--><mdd:PROVPERCENT></mdd:PR
OVPERCENT><!--Optional:--><mdd:PROVAMOUNT></mdd:PROVAMOUNT><!--Optional:--><mdd:PROVCRACCOUNT></mdd:PROVCRACCOUNT><!--Optional:--><mdd:PROVRELDATE></mdd:PROVRELDATE><!--Optional:--><mdd:PROVRELACCOUNT
></mdd:PROVRELACCOUNT><!--Optional:--><mdd:AUTOEXPIRY>No</mdd:AUTOEXPIRY><!--Optional:--><mdd:ALTERNATEID>GRREF</mdd:ALTERNATEID><!--Optional:--><mdd:LIQUIDATIONMODE>Manual</mdd:LIQUIDATIONMODE><!--Op
tional:--><mdd:EVENTSPROCESSING>Online</mdd:EVENTSPROCESSING><!--Optional:--><mdd:SLREFTRANCHE></mdd:SLREFTRANCHE><!--Optional:--><mdd:SLPRODTYPE></mdd:SLPRODTYPE><!--Optional:--><mdd:SLLINKDATE></mdd
:SLLINKDATE><!--Optional:--><mdd:RATECHANGE></mdd:RATECHANGE><!--Optional:--><mdd:NEWCSNRATE></mdd:NEWCSNRATE><!--Optional:--><mdd:NEWRATEEFFDATE></mdd:NEWRATEEFFDATE><!--Optional:--><mdd:RETURNCOMM><
/mdd:RETURNCOMM><!--Optional:--><mdd:ADVICEEXPIRYDATE>20171220</mdd:ADVICEEXPIRYDATE><!--Optional:--><mdd:PROVEXCHRATE></mdd:PROVEXCHRATE><!--Optional:--><mdd:CSNCLAIM></mdd:CSNCLAIM></MDDEALGTISS1Typ
e></bgis:BgIssue></soapenv:Body></soapenv:Envelope>
test1----->>>>>>> {"S:Envelope":{"$":{"xmlns:S":"http://schemas.xmlsoap.org/soap/envelope/"},"S:Body":[{"ns4:BgIssueResponse":[{"$":{"xmlns:ns4":"http://temenos.com/BgIssue","xmlns:ns3":"http://temeno
s.com/MDDEALGTISS1","xmlns:ns2":"http://temenos.com/MDDEAL"},"Status":[{"transactionId":["MD1511222217"],"messageId":[""],"successIndicator":["T24Error"],"application":["NO"],"messages":["AUTO.EXPIRY:
1:1=NO SPECIFIED VALUE"]}]}]}]}}
test------>>>>>>>> { 'S:Envelope':
{ '$': { 'xmlns:S': 'http://schemas.xmlsoap.org/soap/envelope/' },
'S:Body': [ [Object] ] } }
transactionId [ 'MD1511222217' ]
TransactionID MD1511222217

## 11
[ibc-js] GetCustomerBasedRecords - success: { jsonrpc: '2.0', result: { status: 'OK' }, id: 1513686723336 }